## tasks
Tasks
Id | Summary | Is blocked by | Comments | Min | Normal | Max
TASK-1 | Base functionality implementations. |  |  | 3 | 5 | 13
TASK-2 | First page implementation. | TASK-1 |  | 1 | 3 | 8
TASK-3 | Popup implementation. | TASK-1 | Why is it here?
TASK-4 | Integration tests for first page and popup. | TASK-2,TASK-3 |  | 5 | 13 | 20
Some other tasks
TASK-5 | Cart calculation logic - Part 1 |  |  | 13 | 20 | 40
TASK-6 | Second page implementation. | TASK-2 | Need to be investigated. |  | 40